## View
Application Name | TEI | TEI Override | Final TCI | Planning Period | Total KT Period | Plan Start | Plan End | KA Start | KA End | Shadow Start | Shadow End | Rev Start | Rev End | Go Live | 25-Dec | 01-Jan | 08-Jan | 15-Jan | 22-Jan | 29-Jan | 05-Feb | 12-Feb | 19-Feb | 26-Feb | 04-Mar | 11-Mar | 18-Mar | 25-Mar | 01-Apr | 08-Apr
BAU - Platform Modernization | 3 | 3 | 5 | 3 | 12 | 25-Dec-23 | 12-Jan-24 | 15-Jan-24 | 23-Feb-24 | 26-Feb-24 | 15-Mar-24 | 18-Mar-24 | 7-Apr-24 | 8-Apr-24 | Planning |  |  | Knowledge Acquisition | [5 empty] | Shadow |  |  | Rev Shadow |  |  | Live
Dynamic365 | 3 | 3 | 4 | 3 | 10 | 8-Jan-24 | 26-Jan-24 | 29-Jan-24 | 1-Mar-24 | 4-Mar-24 | 17-Mar-24 | 18-Mar-24 | 7-Apr-24 | 8-Apr-24 |  |  | Planning |  |  | Knowledge Acquisition |  |  |  |  | Shadow |  | Rev Shadow |  |  | Live
Crump ACE Case | 4 | 4 | 3 | 2 | 8 | 25-Dec-23 | 5-Jan-24 | 8-Jan-24 | 2-Feb-24 | 5-Feb-24 | 16-Feb-24 | 19-Feb-24 | 3-Mar-24 | 4-Mar-24 | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Tapsys2006 Shell | 3 | 3 | 3 | 2 | 8 | 1-Jan-24 | 12-Jan-24 | 15-Jan-24 | 9-Feb-24 | 12-Feb-24 | 23-Feb-24 | 26-Feb-24 | 10-Mar-24 | 11-Mar-24 |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Agency Management | 2 | 4 | 3 | 2 | 8 | 8-Jan-24 | 19-Jan-24 | 22-Jan-24 | 16-Feb-24 | 19-Feb-24 | 1-Mar-24 | 4-Mar-24 | 17-Mar-24 | 18-Mar-24 |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Agency Portal | 2 | 3 | 3 | 2 | 8 | 15-Jan-24 | 26-Jan-24 | 29-Jan-24 | 23-Feb-24 | 26-Feb-24 | 8-Mar-24 | 11-Mar-24 | 24-Mar-24 | 25-Mar-24 |  |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Compliance | 2 | 2 | 2 | 1 | 6 | 5-Feb-24 | 9-Feb-24 | 12-Feb-24 | 1-Mar-24 | 4-Mar-24 | 10-Mar-24 | 11-Mar-24 | 24-Mar-24 | 25-Mar-24 | [6 empty] | Planning | Knowledge Acquisition |  |  | Shadow | Rev Shadow |  | Live
Document Server | 2 | 2 | 1 | 1 | 4 | 4-Mar-24 | 8-Mar-24 | 11-Mar-24 | 22-Mar-24 | 25-Mar-24 | 29-Mar-24 | 1-Apr-24 | 7-Apr-24 | 8-Apr-24 | [10 empty] | Planning | Knowledge Acquisition |  | Shadow | Rev Shadow | Live
Insurance Portal | 2 | 2 | 5 | 3 | 12 | 25-Dec-23 | 12-Jan-24 | 15-Jan-24 | 23-Feb-24 | 26-Feb-24 | 15-Mar-24 | 18-Mar-24 | 7-Apr-24 | 8-Apr-24 | Planning |  |  | Knowledge Acquisition | [5 empty] | Shadow |  |  | Rev Shadow |  |  | Live
SSRS Reports | 2 | 2 | 4 | 3 | 10 | 1-Jan-24 | 19-Jan-24 | 22-Jan-24 | 23-Feb-24 | 26-Feb-24 | 10-Mar-24 | 11-Mar-24 | 30-Mar-24 | 1-Apr-24 |  | Planning |  |  | Knowledge Acquisition |  |  |  |  | Shadow |  | Rev Shadow |  |  | Live
Tapco Web Portal | 2 | 2 | 3 | 2 | 8 | 22-Jan-24 | 2-Feb-24 | 5-Feb-24 | 1-Mar-24 | 4-Mar-24 | 15-Mar-24 | 18-Mar-24 | 30-Mar-24 | 1-Apr-24 |  |  |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Tapsys2006 | 2 | 2 | 3 | 2 | 8 | 29-Jan-24 | 9-Feb-24 | 12-Feb-24 | 8-Mar-24 | 11-Mar-24 | 22-Mar-24 | 25-Mar-24 | 7-Apr-24 | 8-Apr-24 | [5 empty] | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Agency Workspace – Salesforce Experience Cloud | 0 |  | 3 | 2 | 8 | 29-Jan-24 | 9-Feb-24 | 12-Feb-24 | 8-Mar-24 | 11-Mar-24 | 22-Mar-24 | 25-Mar-24 | 7-Apr-24 | 8-Apr-24 | [5 empty] | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
BenAdmin EmployerFocus | 0 |  | 3 | 2 | 8 | 29-Jan-24 | 9-Feb-24 | 12-Feb-24 | 8-Mar-24 | 11-Mar-24 | 22-Mar-24 | 25-Mar-24 | 7-Apr-24 | 8-Apr-24 | [5 empty] | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
BenAdmin BenefitMall Administration System | 0 |  | 2 | 1 | 6 | 19-Feb-24 | 23-Feb-24 | 26-Feb-24 | 15-Mar-24 | 18-Mar-24 | 24-Mar-24 | 25-Mar-24 | 7-Apr-24 | 8-Apr-24 | [8 empty] | Planning | Knowledge Acquisition |  |  | Shadow | Rev Shadow |  | Live
BenAdmin Rules Based System | 0 |  | 1 | 1 | 4 | 26-Feb-24 | 1-Mar-24 | 4-Mar-24 | 15-Mar-24 | 18-Mar-24 | 22-Mar-24 | 25-Mar-24 | 30-Mar-24 | 1-Apr-24 | [9 empty] | Planning | Knowledge Acquisition |  | Shadow | Rev Shadow | Live
BenAdmin Carrier Extract Transform Load | 0 |  | 5 | 3 | 12 | 25-Dec-23 | 12-Jan-24 | 15-Jan-24 | 23-Feb-24 | 26-Feb-24 | 15-Mar-24 | 18-Mar-24 | 7-Apr-24 | 8-Apr-24 | Planning |  |  | Knowledge Acquisition | [5 empty] | Shadow |  |  | Rev Shadow |  |  | Live
BenAdmin Enhanced-Billing Generation App | 0 |  | 4 | 3 | 10 | 25-Dec-23 | 12-Jan-24 | 15-Jan-24 | 16-Feb-24 | 19-Feb-24 | 3-Mar-24 | 4-Mar-24 | 24-Mar-23 | 25-Mar-24 | Planning |  |  | Knowledge Acquisition |  |  |  |  | Shadow |  | Rev Shadow |  |  | Live
BenAdmin New Hire/Employee Onboarding | 0 |  | 3 | 2 | 8 | 22-Jan-24 | 2-Feb-24 | 5-Feb-24 | 1-Mar-24 | 4-Mar-24 | 15-Mar-24 | 18-Mar-24 | 30-Mar-24 | 1-Apr-24 |  |  |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
BenAdmin ReportX | 0 |  | 3 | 2 | 8 | 15-Jan-24 | 26-Jan-24 | 29-Jan-24 | 23-Feb-24 | 26-Feb-24 | 8-Mar-24 | 11-Mar-24 | 24-Mar-24 | 25-Mar-24 |  |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Integration Hub | 0 |  | 3 | 2 | 8 | 1-Jan-24 | 12-Jan-24 | 15-Jan-24 | 9-Feb-24 | 12-Feb-24 | 23-Feb-24 | 26-Feb-24 | 10-Mar-24 | 11-Mar-24 |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Online Enrollment | 0 |  | 3 | 2 | 8 | 8-Jan-24 | 19-Jan-24 | 22-Jan-24 | 16-Feb-24 | 19-Feb-24 | 1-Mar-24 | 4-Mar-24 | 17-Mar-24 | 18-Mar-24 |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live
Cloud API Integrator | 3 | 3 | 2 | 1 | 6 | 12-Feb-24 | 16-Feb-24 | 19-Feb-24 | 8-Mar-24 | 11-Mar-24 | 17-Mar-24 | 18-Mar-24 | 30-Mar-24 | 1-Apr-24 | [7 empty] | Planning | Knowledge Acquisition |  |  | Shadow | Rev Shadow |  | Live
Fusion | 3 | 3 | 3 | 2 | 8 | 22-Jan-24 | 2-Feb-24 | 5-Feb-24 | 1-Mar-24 | 4-Mar-24 | 15-Mar-24 | 18-Mar-24 | 30-Mar-24 | 1-Apr-24 |  |  |  |  | Planning |  | Knowledge Acquisition |  |  |  | Shadow |  | Rev Shadow |  | Live